## Dashboard
CloudOps Hub - Risk Management Dashboard
Overview & Top Risks Summary
Total Risks | Critical Risks (Score ≥ 6) | Moderate/Low Risks
16 | 8 | 8
Top Risks Requiring Immediate Attention (Score ≥ 6)
Risk ID | Category | Risk Name | Probability | Impact | Risk Score | Risk Level
R001 | Technical Risks | Scope Creep | 3 | 3 | 9 | Critical
R011 | Project Management Risks | Insufficient Development Time | 3 | 3 | 9 | Critical
R002 | Technical Risks | Monitoring Agent Complexity | 2 | 3 | 6 | Critical
R005 | Cloud & Infrastructure Risks | Lack of Azure/AWS Access | 3 | 2 | 6 | Critical
R008 | Security Risks | Sensitive Data Exposure | 2 | 3 | 6 | Critical
R009 | Security Risks | Authentication Vulnerabilities | 2 | 3 | 6 | Critical
R013 | Project Management Risks | Poor Documentation | 3 | 2 | 6 | Critical
R016 | Academic Risks | Failure to Meet Capstone Requirements | 2 | 3 | 6 | Critical

## Risk Register
CloudOps Hub - Risk Register
Project Type: Cloud-Native Monitoring and Operations Platform ¦ Prepared By: Capstone Team
Risk ID | Category | Risk Name | Description | Probability | Impact | Risk Score | Risk Level | Mitigation Strategy | Contingency Plan
R001 | Technical Risks | Scope Creep | Additional features are continuously added during development, increasing complexity and jeopardizing project completion. | 3 | 3 | 9 | Critical | Define a strict MVP Place all non-essential features into a Future Enhancements backlog Require team approval before accepting new features | Remove stretch goals and focus on core monitoring functionality.
R002 | Technical Risks | Monitoring Agent Complexity | Data collection agents may become more difficult to implement than anticipated across various operating systems and devices. | 2 | 3 | 6 | Critical | Start with Linux monitoring only Use existing APIs or open-source exporters where possible Standardize collected metrics | Use simulated devices or pre-existing monitoring exporters.
R003 | Technical Risks | Integration Challenges | Third-party integrations such as Proxmox, Docker, Unraid, or NAS systems may present compatibility issues. | 2 | 2 | 4 | High | Build platform-independent monitoring first Treat integrations as stretch goals | Demonstrate functionality using generic Linux systems.
R004 | Technical Risks | Database Design Errors | Poor schema design may impact scalability or require significant redesign later. | 2 | 2 | 4 | High | Perform design reviews prior to implementation Build ERD before development Normalize core entities | Refactor database and migrate data structures.
R005 | Cloud & Infrastructure Risks | Lack of Azure/AWS Access | Cloud resources may not be available early in the project. | 3 | 2 | 6 | Critical | Develop locally using Docker Use Terraform modules without deployment Use free-tier accounts later | Deploy proof-of-concept locally and present cloud-ready architecture.
R006 | Cloud & Infrastructure Risks | Unexpected Cloud Costs | Monitoring workloads could exceed free-tier limits. | 2 | 2 | 4 | High | Use budgets and alerts Minimize ingestion volume Remove unnecessary telemetry | Migrate portions to local infrastructure.
R007 | Cloud & Infrastructure Risks | Infrastructure Deployment Failure | Terraform or deployment automation could fail due to configuration errors. | 2 | 2 | 4 | High | Use version-controlled IaC Test deployments in small environments | Deploy using manual procedures while troubleshooting.
R008 | Security Risks | Sensitive Data Exposure | Credentials, API keys, or secrets could accidentally be stored in source control. | 2 | 3 | 6 | Critical | Use environment variables Implement secret scanning Use secret management tools | Rotate compromised credentials immediately.
R009 | Security Risks | Authentication Vulnerabilities | Improper authentication implementation may expose accounts. | 2 | 3 | 6 | Critical | Use proven authentication frameworks Follow OWASP recommendations Test authorization policies | Temporarily disable affected functionality until corrected.
R010 | Security Risks | Unauthorized Access to Monitoring Data | Users may gain access to resources belonging to other users. | 1 | 3 | 3 | Moderate | Implement RBAC Separate tenant data Test permissions extensively | Restrict account access and correct permission models.
R011 | Project Management Risks | Insufficient Development Time | Project effort exceeds available academic term. | 3 | 3 | 9 | Critical | Maintain MVP focus Time-box development phases Prioritize core requirements | Remove non-essential features and integrations.
R012 | Project Management Risks | Team Availability | Team members may become unavailable due to coursework, work obligations, or illness. | 2 | 2 | 4 | High | Share responsibilities Maintain documentation Conduct regular progress reviews | Redistribute work among remaining members.
R013 | Project Management Risks | Poor Documentation | Documentation may fall behind development activities. | 3 | 2 | 6 | Critical | Document features as they are completed Assign documentation ownership | Dedicate final project phase exclusively to documentation.
R014 | Operational Risks | Alert Fatigue | Excessive notifications may reduce the usefulness of alerting. | 2 | 2 | 4 | High | Define meaningful thresholds Implement alert suppression rules Prioritize critical alerts | Reduce alert frequency and increase thresholds.
R015 | Operational Risks | System Performance Issues | Dashboard or API performance may degrade as monitored devices increase. | 2 | 2 | 4 | High | Optimize database queries Use caching where appropriate Limit MVP scale assumptions | Reduce monitoring frequency and archive historical data.
R016 | Academic Risks | Failure to Meet Capstone Requirements | Project implementation may not adequately demonstrate required cloud concepts. | 2 | 3 | 6 | Critical | Map every deliverable to course outcomes: • Security • Monitoring • Automation • Business continuity • Well-Architected Framework • CI/CD | Develop supplementary documentation and demonstrations.

## Rating Scales
Risk Rating Scales
Probability Scale |  |  | Impact Scale
Level | Score | Description | Level | Score | Description
Low | 1 | Unlikely to occur | Low | 1 | Minor project disruption
Medium | 2 | Could occur | Medium | 2 | Noticeable delay or reduction in scope
High | 3 | Likely to occur | High | 3 | Major impact on project success